## Module B Staggering
Module B - Staggering
© CC-BY-SA 2022 Blue-Dolphin.World / Wolfram Müller |  | netto ConstraintCapacity | [5 empty] | StartDate
|  | 20 | [5 empty] | 2022-01-17 | Timeline
 | time axis 2022-01-17 to 2022-06-02
|  | … Durations in Wokring Days … |  |  | ProjectPhaseTimings | time axis 2022-01-17 to 2022-06-02
Projekt | LeadDuration | ConstraintDuration | LagDuration | WishDate | ProjectStart | ConstraintStart | ConstraintEnd | ProjectEnd | time axis 2022-01-17 to 2022-06-02
PRJ_Nil | 61 | 81 | 8 |  | 2021-10-22 | 2022-01-17 | 2022-05-10 | 2022-05-20 | bar: 2022-01-17 to 2022-05-19
PRJ_Amazonas | 43 | 57 | 6 |  | 2021-11-23 | 2022-01-21 | 2022-04-12 | 2022-04-20 | bar: 2022-01-17 to 2022-04-19
PRJ_Jangtsekiang | 31 | 41 | 4 |  | 2021-12-13 | 2022-01-25 | 2022-03-23 | 2022-03-29 | bar: 2022-01-17 to 2022-03-28
PRJ_Mississippi | 17 | 0 | 17 | 2022-01-26 05:32 | 2021-12-09 | 2022-01-03 | 2022-01-03 | 2022-01-26 | bar: 2022-01-17 to 2022-01-25
PRJ_Jenissei | 34 | 45 | 5 |  | 2021-12-10 | 2022-01-27 | 2022-03-31 | 2022-04-07 | bar: 2022-01-17 to 2022-04-06
PRJ_Ob | 2 | 0 | 2 | 2022-02-04 11:05 | 2022-01-31 | 2022-02-02 | 2022-02-02 | 2022-02-04 | bar: 2022-01-31 to 2022-02-03
PRJ_Amur | 76 | 101 | 10 |  | 2021-10-18 | 2022-02-01 | 2022-06-22 | 2022-07-06 | bar: 2022-01-17 to 2022-06-02
PRJ_HwangHo | 14 | 18 | 2 |  | 2022-01-19 | 2022-02-08 | 2022-03-04 | 2022-03-08 | bar: 2022-01-19 to 2022-03-07
PRJ_Kongo | 5 | 7 | 1 |  | 2022-02-02 | 2022-02-09 | 2022-02-18 | 2022-02-21 | bar: 2022-02-02 to 2022-02-20
PRJ_Mekong | 2 | 3 | 1 |  | 2022-02-07 | 2022-02-09 | 2022-02-14 | 2022-02-15 | bar: 2022-02-07 to 2022-02-14
PRJ_Lena | 4 | 5 | 1 |  | 2022-02-03 | 2022-02-09 | 2022-02-16 | 2022-02-17 | bar: 2022-02-03 to 2022-02-16
PRJ_Mackenzie | 55 | 73 | 7 |  | 2021-11-24 | 2022-02-09 | 2022-05-23 | 2022-06-01 | bar: 2022-01-17 to 2022-05-31
PRJ_Niger | 32 | 0 | 32 | 2022-02-13 16:37 | 2021-11-16 | 2021-12-30 | 2021-12-30 | 2022-02-14 | bar: 2022-01-17 to 2022-02-13
PRJ_Parana | 56 | 75 | 8 |  | 2021-11-29 | 2022-02-15 | 2022-05-31 | 2022-06-10 | bar: 2022-01-17 to 2022-06-02
PRJ_MurrayRiver | 13 | 0 | 13 | 2022-03-04 03:42 | 2022-01-27 | 2022-02-15 | 2022-02-15 | 2022-03-04 | bar: 2022-01-27 to 2022-03-03
PRJ_Schatt-al-Arab | 2 | 0 | 2 | 2022-02-22 22:09 | 2022-02-16 | 2022-02-18 | 2022-02-18 | 2022-02-22 | bar: 2022-02-16 to 2022-02-21
PRJ_Wolga | 95 | 127 | 13 |  | 2021-10-11 | 2022-02-21 | 2022-08-17 | 2022-09-05 | bar: 2022-01-17 to 2022-06-02
PRJ_Meghna | 86 | 114 | 11 |  | 2021-11-01 | 2022-03-01 | 2022-08-08 | 2022-08-23 | bar: 2022-01-17 to 2022-06-02
PRJ_RioSaoFrancisco | 32 | 43 | 4 |  | 2022-01-24 | 2022-03-09 | 2022-05-09 | 2022-05-13 | bar: 2022-01-24 to 2022-05-12
PRJ_Yukon | 91 | 121 | 12 |  | 2021-11-04 | 2022-03-11 | 2022-08-29 | 2022-09-14 | bar: 2022-01-17 to 2022-06-02
PRJ_Indus | 1 | 0 | 1 | 2022-03-13 09:14 | 2022-03-10 | 2022-03-11 | 2022-03-11 | 2022-03-14 | bar: 2022-03-10 to 2022-03-13
PRJ_RioGrande | 30 | 100 | 10 |  | 2022-02-07 | 2022-03-21 | 2022-08-08 | 2022-08-22 | bar: 2022-02-07 to 2022-06-02
PRJ_Syrdarja | 1 | 0 | 1 | 2022-03-22 14:46 | 2022-03-18 | 2022-03-21 | 2022-03-21 | 2022-03-22 | bar: 2022-03-18 to 2022-03-21
PRJ_Orinoco | 29 | 38 | 4 |  | 2022-02-15 | 2022-03-28 | 2022-05-19 | 2022-05-25 | bar: 2022-02-15 to 2022-05-24
PRJ_Saluen | 1 | 0 | 1 | 2022-03-31 20:18 | 2022-03-29 | 2022-03-30 | 2022-03-30 | 2022-03-31 | bar: 2022-03-29 to 2022-03-30
PRJ_Donau | 13 | 17 | 2 |  | 2022-03-11 | 2022-03-30 | 2022-04-22 | 2022-04-26 | bar: 2022-03-11 to 2022-04-25
PRJ_Amudarja | 3 | 4 | 0 |  | 2022-03-28 | 2022-03-31 | 2022-04-06 | 2022-04-06 | bar: 2022-03-28 to 2022-04-05
PRJ_NelsonRiver | 25 | 33 | 3 |  | 2022-02-24 | 2022-03-31 | 2022-05-17 | 2022-05-20 | bar: 2022-02-24 to 2022-05-19
PRJ_Sambesi | 5 | 0 | 2 | 2022-04-10 01:51 | 2022-03-31 | 2022-04-07 | 2022-04-07 | 2022-04-11 | bar: 2022-03-31 to 2022-04-10
PRJ_Kolyma | 5 | 0 | 5 | 2022-04-19 07:23 | 2022-04-05 | 2022-04-12 | 2022-04-12 | 2022-04-19 | bar: 2022-04-05 to 2022-04-18
PRJ_RioTocantins | 68 | 0 | 68 | 2022-04-28 12:55 | 2021-10-20 | 2022-01-24 | 2022-01-24 | 2022-04-28 | bar: 2022-01-17 to 2022-04-27
PRJ_Ural | 80 | 0 | 20 | 2022-05-07 18:28 | 2021-12-20 | 2022-04-11 | 2022-04-11 | 2022-05-09 | bar: 2022-01-17 to 2022-05-08
PRJ_Sankt-Lorenz-Strom | 37 | 0 | 37 | 2022-05-17 | 2022-02-01 | 2022-03-24 | 2022-03-24 | 2022-05-16 | bar: 2022-02-01 to 2022-05-15

## Module C Execution Management
Module C - Execution Management
© CC-BY-SA 2022 Blue-Dolphin.World / Wolfram Müller | [5 empty] | StatusDatum
2022-02-02
Data from Staggering (Module B) | Touches | ProjectPhaseTimings |  |  |  | Project Status |  |  |  |  | Open-Item-List
Project | Constraint | ProjectStart | ConstraintStart | ConstraintEnd | ProjectEnd | CurrentPhase | ID | PlannedPhase | ID | Message | Root-Cause of the Delay/Problem | Solution/BufferRegain Meassure | Responsible | DueDate
PRJ_Nil | yes | 2021-10-22 | 2022-01-17 | 2022-05-10 | 2022-05-20 | BC - Lead - before Constraint or 50% | 1 | IC - In Constraint | 2 | Project is in Staus [BC - Lead - before Constraint or 50%] but should be in [IC - In Constraint] | External Supplier XXX delay of Delivery of Controller YYY by 14 Days | Evaluation of Second Source to be faster | Franz Karl Weber | 2022-04-19 | Phases | Order
PRJ_Amazonas | yes | 2021-11-23 | 2022-01-21 | 2022-04-12 | 2022-04-20 | NS - Not Started | 0 | IC - In Constraint | 2 | Project is in Staus [NS - Not Started] but should be in [IC - In Constraint] | … |  |  |  | NS - Not Started | 0
PRJ_Jangtsekiang | yes | 2021-12-13 | 2022-01-25 | 2022-03-23 | 2022-03-29 | NS - Not Started | 0 | IC - In Constraint | 2 | Project is in Staus [NS - Not Started] but should be in [IC - In Constraint] |  |  |  |  | BC - Lead - before Constraint or 50% | 1
PRJ_Mississippi | no | 2021-12-10 | 2022-01-27 | 2022-03-31 | 2022-04-07 | AC - Lag - after Constraint or 50% | 3 | AC - Lag - after Constraint or 50% | 3 | - |  |  |  |  | IC - In Constraint | 2
PRJ_Jenissei | yes | 2021-10-18 | 2022-02-01 | 2022-06-22 | 2022-07-06 | NS - Not Started | 0 | IC - In Constraint | 2 | Project is in Staus [NS - Not Started] but should be in [IC - In Constraint] |  |  |  |  | AC - Lag - after Constraint or 50% | 3
PRJ_Ob | yes | 2022-01-19 | 2022-02-08 | 2022-03-04 | 2022-03-08 | NS - Not Started | 0 | BC - Lead - before Constraint or 50% | 1 | Project is in Staus [NS - Not Started] but should be in [BC - Lead - before Constraint or 50%] |  |  |  |  | FN - Finished | 4
PRJ_Amur | no | 2022-02-02 | 2022-02-09 | 2022-02-18 | 2022-02-21 | NS - Not Started | 0 | BC - Lead - before Constraint or 50% | 1 | Project is in Staus [NS - Not Started] but should be in [BC - Lead - before Constraint or 50%]
PRJ_HwangHo | yes | 2022-02-07 | 2022-02-09 | 2022-02-14 | 2022-02-15 | NS - Not Started | 0 | NS - Not Started | 0 | -
PRJ_Kongo | no | 2022-02-03 | 2022-02-09 | 2022-02-16 | 2022-02-17 | NS - Not Started | 0 | NS - Not Started | 0 | -
PRJ_Mekong | no | 2021-11-24 | 2022-02-09 | 2022-05-23 | 2022-06-01 | NS - Not Started | 0 | BC - Lead - before Constraint or 50% | 1 | Project is in Staus [NS - Not Started] but should be in [BC - Lead - before Constraint or 50%]
PRJ_Lena | no | 2021-11-29 | 2022-02-15 | 2022-05-31 | 2022-06-10 | NS - Not Started | 0 | BC - Lead - before Constraint or 50% | 1 | Project is in Staus [NS - Not Started] but should be in [BC - Lead - before Constraint or 50%]
PRJ_Mackenzie | no | 2021-10-11 | 2022-02-21 | 2022-08-17 | 2022-09-05 | NS - Not Started | 0 | BC - Lead - before Constraint or 50% | 1 | Project is in Staus [NS - Not Started] but should be in [BC - Lead - before Constraint or 50%]
PRJ_Niger | no | 2021-11-01 | 2022-03-01 | 2022-08-08 | 2022-08-23 | BC - Lead - before Constraint or 50% | 1 | BC - Lead - before Constraint or 50% | 1 | -
PRJ_Parana | yes | 2022-01-24 | 2022-03-09 | 2022-05-09 | 2022-05-13 | NS - Not Started | 0 | BC - Lead - before Constraint or 50% | 1 | Project is in Staus [NS - Not Started] but should be in [BC - Lead - before Constraint or 50%]
PRJ_MurrayRiver | yes | 2021-11-04 | 2022-03-11 | 2022-08-29 | 2022-09-14 | NS - Not Started | 0 | BC - Lead - before Constraint or 50% | 1 | Project is in Staus [NS - Not Started] but should be in [BC - Lead - before Constraint or 50%]
PRJ_Schatt-al-Arab | no | 2022-02-07 | 2022-03-21 | 2022-08-08 | 2022-08-22 | NS - Not Started | 0 | NS - Not Started | 0 | -
PRJ_Wolga | yes | 2022-02-15 | 2022-03-28 | 2022-05-19 | 2022-05-25 | NS - Not Started | 0 | NS - Not Started | 0 | -
PRJ_Meghna | yes | 2022-03-11 | 2022-03-30 | 2022-04-22 | 2022-04-26 | IC - In Constraint | 2 | NS - Not Started | 0 | Project SHOULD not be started - stop now! | Mr. Meier thought early start is effective | Mr. Müller explains again the latest-possible-start | Mr. Müller | 2022-04-20
PRJ_RioSaoFrancisco | yes | 2022-03-28 | 2022-03-31 | 2022-04-06 | 2022-04-06 | NS - Not Started | 0 | NS - Not Started | 0 | -
PRJ_Yukon | yes | 2022-02-24 | 2022-03-31 | 2022-05-17 | 2022-05-20 | NS - Not Started | 0 | NS - Not Started | 0 | -
PRJ_Indus | yes | 2021-12-09 | 2022-01-03 | 2022-01-03 | 2022-01-26 | IC - In Constraint | 2 | FN - Finished | 4 | Project is in Staus [IC - In Constraint] but should be in [FN - Finished]
PRJ_RioGrande | yes | 2022-01-31 | 2022-02-02 | 2022-02-02 | 2022-02-04 | NS - Not Started | 0 | AC - Lag - after Constraint or 50% | 3 | Project is in Staus [NS - Not Started] but should be in [AC - Lag - after Constraint or 50%]
PRJ_Syrdarja | yes | 2021-11-16 | 2021-12-30 | 2021-12-30 | 2022-02-14 | NS - Not Started | 0 | AC - Lag - after Constraint or 50% | 3 | Project is in Staus [NS - Not Started] but should be in [AC - Lag - after Constraint or 50%]
PRJ_Orinoco | no | 2022-02-16 | 2022-02-18 | 2022-02-18 | 2022-02-22 | NS - Not Started | 0 | NS - Not Started | 0 | -
PRJ_Saluen | no | 2022-01-27 | 2022-02-15 | 2022-02-15 | 2022-03-04 | NS - Not Started | 0 | BC - Lead - before Constraint or 50% | 1 | Project is in Staus [NS - Not Started] but should be in [BC - Lead - before Constraint or 50%]
PRJ_Donau | yes | 2022-03-10 | 2022-03-11 | 2022-03-11 | 2022-03-14 | NS - Not Started | 0 | NS - Not Started | 0 | -
PRJ_Amudarja | yes | 2022-03-18 | 2022-03-21 | 2022-03-21 | 2022-03-22 | NS - Not Started | 0 | NS - Not Started | 0 | -
PRJ_NelsonRiver | yes | 2022-03-29 | 2022-03-30 | 2022-03-30 | 2022-03-31 | NS - Not Started | 0 | NS - Not Started | 0 | -
PRJ_Sambesi | yes | 2022-03-31 | 2022-04-07 | 2022-04-07 | 2022-04-11 | NS - Not Started | 0 | NS - Not Started | 0 | -
PRJ_Kolyma | yes | 2022-04-05 | 2022-04-12 | 2022-04-12 | 2022-04-19 | NS - Not Started | 0 | NS - Not Started | 0 | -
PRJ_RioTocantins | yes | 2021-10-20 | 2022-01-24 | 2022-01-24 | 2022-04-28 | NS - Not Started | 0 | AC - Lag - after Constraint or 50% | 3 | Project is in Staus [NS - Not Started] but should be in [AC - Lag - after Constraint or 50%]
PRJ_Ural | no | 2021-12-20 | 2022-04-11 | 2022-04-11 | 2022-05-09 | NS - Not Started | 0 | BC - Lead - before Constraint or 50% | 1 | Project is in Staus [NS - Not Started] but should be in [BC - Lead - before Constraint or 50%]
PRJ_Sankt-Lorenz-Strom | no | 2022-02-01 | 2022-03-24 | 2022-03-24 | 2022-05-16 | NS - Not Started | 0 | BC - Lead - before Constraint or 50% | 1 | Project is in Staus [NS - Not Started] but should be in [BC - Lead - before Constraint or 50%]

## Input from Module A
Project | Active | Constraint | WD in Constraint | WD over all
PRJ_Nil | yes | yes | 81 | 0
PRJ_Amazonas | yes | yes | 57 | 0
PRJ_Jangtsekiang | yes | yes | 41 | 0
PRJ_Mississippi | yes | no | 0 | 3
PRJ_Jenissei | yes | yes | 45 | 0
PRJ_Ob | yes | yes | 101 | 0
PRJ_Amur | yes | no | 0 | 34
PRJ_HwangHo | yes | yes | 18 | 0
PRJ_Kongo | yes | no | 0 | 63
PRJ_Mekong | yes | no | 0 | 4
PRJ_Lena | yes | no | 0 | 25
PRJ_Mackenzie | yes | no | 0 | 2
PRJ_Niger | yes | no | 0 | 1
PRJ_Parana | yes | yes | 7 | 0
PRJ_MurrayRiver | yes | yes | 3 | 0
PRJ_Schatt-al-Arab | yes | no | 0 | 1
PRJ_Wolga | yes | yes | 5 | 0
PRJ_Meghna | yes | yes | 73 | 0
PRJ_RioSaoFrancisco | yes | yes | 75 | 0
PRJ_Yukon | yes | yes | 127 | 0
PRJ_Indus | yes | yes | 0 | 0
PRJ_RioGrande | yes | yes | 114 | 0
PRJ_Syrdarja | yes | yes | 43 | 0
PRJ_Orinoco | yes | no | 0 | 9
PRJ_Saluen | yes | no | 0 | 136
PRJ_Donau | yes | yes | 121 | 0
PRJ_Amudarja | yes | yes | 400 | 0
PRJ_NelsonRiver | yes | yes | 38 | 0
PRJ_Sambesi | yes | yes | 17 | 0
PRJ_Kolyma | yes | yes | 4 | 0
PRJ_RioTocantins | yes | yes | 33 | 0
PRJ_Ural | yes | no | 0 | 99
PRJ_Sankt-Lorenz-Strom | yes | no | 0 | 73
PRJ_ColoradoRiver | no | yes | 0 | 0
PRJ_Olenjok | no | no | 0 | 0
PRJ_ColumbiaRiver | no | no | 0 | 0

## Some Heuristik
Project | WD before Constraint | WD in Constraint | WD after Constaint | is Constrained | Duration before Constraint | Dur. after Constraint
PRJ_Nil | 61 | 81 | 8 | yes | 75% | 10%
PRJ_Amazonas | 43 | 57 | 6 | yes | 75% | 10%
PRJ_Jangtsekiang | 31 | 41 | 4 | yes | 75% | 10%
PRJ_Mississippi | 2 | 0 | 2 | no | 75% | 10%
PRJ_Jenissei | 34 | 45 | 5 | yes | 75% | 10%
PRJ_Ob | 76 | 101 | 10 | yes | 75% | 10%
PRJ_Amur | 17 | 0 | 17 | no | 75% | 10%
PRJ_HwangHo | 14 | 18 | 2 | yes | 75% | 10%
PRJ_Kongo | 32 | 0 | 32 | no | 75% | 10%
PRJ_Mekong | 2 | 0 | 2 | no | 75% | 10%
PRJ_Lena | 13 | 0 | 13 | no | 75% | 10%
PRJ_Mackenzie | 1 | 0 | 1 | no | 75% | 10%
PRJ_Niger | 1 | 0 | 1 | no | 75% | 10%
PRJ_Parana | 5 | 7 | 1 | yes | 75% | 10%
PRJ_MurrayRiver | 2 | 3 | 0 | yes | 75% | 10%
PRJ_Schatt-al-Arab | 1 | 0 | 1 | no | 75% | 10%
PRJ_Wolga | 4 | 5 | 1 | yes | 75% | 10%
PRJ_Meghna | 55 | 73 | 7 | yes | 75% | 10%
PRJ_RioSaoFrancisco | 56 | 75 | 8 | yes | 75% | 10%
PRJ_Yukon | 95 | 127 | 13 | yes | 75% | 10%
PRJ_Indus | 0 | 0 | 0 | yes | 75% | 10%
PRJ_RioGrande | 86 | 114 | 11 | yes | 75% | 10%
PRJ_Syrdarja | 32 | 43 | 4 | yes | 75% | 10%
PRJ_Orinoco | 5 | 0 | 5 | no | 75% | 10%
PRJ_Saluen | 68 | 0 | 68 | no | 75% | 10%
PRJ_Donau | 91 | 121 | 12 | yes | 75% | 10%
PRJ_Amudarja | 300 | 400 | 40 | yes | 75% | 10%
PRJ_NelsonRiver | 29 | 38 | 4 | yes | 75% | 10%
PRJ_Sambesi | 13 | 17 | 2 | yes | 75% | 10%
PRJ_Kolyma | 3 | 4 | 0 | yes | 75% | 10%
PRJ_RioTocantins | 25 | 33 | 3 | yes | 75% | 10%
PRJ_Ural | 50 | 0 | 50 | no | 75% | 10%
PRJ_Sankt-Lorenz-Strom | 37 | 0 | 37 | no | 75% | 10%